## RoughEstimations
SUMMARY:
Effort estimation (Backlog Size): | 150
Confidence Level: | 80%
Expected duration with 0,8 confidence (sprints): | 16
Sprint cost: | 10000
Budget estimation: | 160000
0 risks identified, 0 with high possible impact
Model Parameters
| Mean | Std. Deviation | Comment
Expected Velocity (FTE/week): | 15 | 5
Expected requirements flow (FTE/week): | 4 | 1
Note on B2: This field is calculated as sum of story-point of backlog items (see Backlog Sheet)
Note on B3: This parameter can be adjusted. The model works poorely for very low (<20%) and high (> 80%) probabilities
Note on B6: This field is calculated based on desired confidence level
Note on B12: This parameter reflects expected team velocity (how many story points they could deliver in average)
Note on C12: This parameters reflects standard deviation of the team velocity (how stable their velocity is. Higher values means less stability)
Note on B13: This parameter shows how many additional story points in average customer would return to the backlog after the demo (requirements inflow)
Note on C13: This parameter reflects expected deviation from average requirements inflow

## Backlog
| Estimated cost: | 160000
| Estimated duration: | 16
| Confidence level: | 80%
Phase | Stage | Estimate (SP) |  | Is in scope? Y/N | Comment
Inception | Create architecture concept | 8 | 8 | Y
| Create alternative concept #1 | 16 | 16 | Y
| Create alternative concept #2 | 16 | 16 | Y
0
Elaboration | Create prototype | 8 | 8 | Y
| Develop design prototype #1 | 8 | 8 | Y
| Develop design prototype #2 | 8 | 8 | Y
| Develop design prototype #3 | 8 | 8 | Y
Construction | Implement User Story 1 | 2 | 2 | Y
| Implement User Story 2 | 4 | 4 | Y
| Implement User Story 3 | 8 | 8 | Y
| Implement User Story 4 | 16 | 16 | Y
| Implement User Story 5 | 2 | 2 | Y
| Implement User Story 6 | 4 | 4 | Y
| Implement User Story 7 | 8 | 8 | Y
| Implement User Story 8 | 16 | 0 | N
| Implement User Story 9 | 2 | 2 | Y
| Implement User Story 10 | 4 | 0 | N
0
0
0
0
0
0
0
0
0
Transition | Documentation development | 16 | 16 | Y
| Release | 16 | 16 | Y
0
0
0
| TOTAL: | 150

## Risks
RISKS
Risk Description | Probability | Impact | Comment

## Calcs
| N | Cumulative | Probability | Risk Tolerance
0 | 1 | 0 | 0 | 0.8 | 11 | 5.099
0 | 2 | 0 | 0 | 0.8 | 22 | 7.2111
0 | 3 | 0 | 0 | 0.8 | 33 | 8.8318
0 | 4 | 0 | 0 | 0.8 | 44 | 10.198
0 | 5 | 0 | 0 | 0.8 | 55 | 11.4018
0 | 6 | 8.7566e-12 | 8.7566e-12 | 0.8 | 66 | 12.49
0 | 7 | 3.1316e-08 | 3.1307e-08 | 0.8 | 77 | 13.4907
0 | 8 | 8.5814e-06 | 8.5501e-06 | 0.8 | 88 | 14.4222
0 | 9 | 0.00042807 | 0.00041949 | 0.8 | 99 | 15.2971
0 | 10 | 0.0065563 | 0.0061283 | 0.8 | 110 | 16.1245
0 | 11 | 0.04319 | 0.036634 | 0.8 | 121 | 16.9115
0 | 12 | 0.15409 | 0.1109 | 0.8 | 132 | 17.6635
0 | 13 | 0.35169 | 0.1976 | 0.8 | 143 | 18.3848
0 | 14 | 0.58303 | 0.23134 | 0.8 | 154 | 19.0788
0 | 15 | 0.77624 | 0.19321 | 0.8 | 165 | 19.7484
1 | 16 | 0.8988 | 0.12256 | 0.8 | 176 | 20.3961
0 | 17 | 0.96079 | 0.061987 | 0.8 | 187 | 21.0238
0 | 18 | 0.98675 | 0.025961 | 0.8 | 198 | 21.6333
0 | 19 | 0.99603 | 0.0092793 | 0.8 | 209 | 22.2261
0 | 20 | 0.99893 | 0.0028995 | 0.8 | 220 | 22.8035
0 | 21 | 0.99974 | 0.0008077 | 0.8 | 231 | 23.3666
0 | 22 | 0.99994 | 0.0002038 | 0.8 | 242 | 23.9165
0 | 23 | 0.99999 | 4.72e-05 | 0.8 | 253 | 24.454
0 | 24 | 1 | 1.0143e-05 | 0.8 | 264 | 24.98
0 | 25 | 1 | 2.0414e-06 | 0.8 | 275 | 25.4951
0 | 26 | 1 | 3.8775e-07 | 0.8 | 286 | 26
0 | 27 | 1 | 6.9968e-08 | 0.8 | 297 | 26.4953
0 | 28 | 1 | 1.2062e-08 | 0.8 | 308 | 26.9815
0 | 29 | 1 | 1.9963e-09 | 0.8 | 319 | 27.4591
0 | 30 | 1 | 3.1851e-10 | 0.8 | 330 | 27.9285
0 | 31 | 1 | 4.9168e-11 | 0.8 | 341 | 28.3901